Castlegate Civils Ltd

# Progress Meeting No. 10 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0010 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 14 August 2025 |

| Meeting date | 14 August 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers; David Okafor, Project Engineer, Arden Moss Consulting Engineers |
| Apologies | Ryan Doyle, Piling Supervisor, Castlegate Civils Ltd |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 10.1 | Health and safety | No incidents this period. | - | - | - |
| 10.2 | Programme | Recovery programme accepted. Earthworks now one week behind. | - | - | - |
| 10.3 | River Kest Bridge - east abutment piling | RFI-0012 is closed. Revised drawings C02 and the pile schedule were issued on 10 July and the check certificate was reissued on 8 July. The piling method statement was approved with comments on 8 August. Piling at the east abutment resumed on 11 August with 24 m piles. | - | - | - |
| 10.4 | Mill Lane culvert | Response from Northvale Water on the water main level is still awaited. | Chase Northvale Water | TR | 21/08/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; DO = David Okafor; RD = Ryan Doyle