Castlegate Civils Ltd

Helen Marsh
Project Manager
Northvale County Council

Our ref: KVL-CGC-100-LT-G-0021
Date: 15 April 2025

Dear Helen,

Early warning - possible delay to the telecom duct diversion

OpenLine Telecom has scheduled its duct diversion between Ch 3+000 and Ch 3+200 for June 2025, later than the May date in our programme.

This may delay earthworks in that length by up to three weeks. We propose to resequence the earthworks to work elsewhere first.

Yours sincerely,

Mark Bellamy, Project Manager, Castlegate Civils Ltd

cc: Tom Reddy, Highways Engineer, Northvale County Council