Castlegate Civils Ltd

# Progress Meeting No. 3 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0003 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 3 April 2025 |

| Meeting date | 3 April 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Chris Moran, Commercial Manager, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Nadia Hussain, Highways Engineer, Arden Moss Consulting Engineers |
| Apologies | David Okafor, Project Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Health and safety | One near miss with a dumper at the compound gate. Banksman now in place. | - | - | - |
| 3.2 | Earthworks | Topsoil strip starts 7 April. Capping source submittal to follow in May. | - | - | - |
| 3.3 | Utilities | Northgrid 11 kV cable diversion under way; energisation planned for May. | Confirm energisation date with Northgrid | TR | 24/04/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; CM = Chris Moran; HM = Helen Marsh; TR = Tom Reddy; NH = Nadia Hussain; DO = David Okafor