Castlegate Civils Ltd

# Progress Meeting No. 4 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0004 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 24 April 2025 |

| Meeting date | 24 April 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Ryan Doyle, Piling Supervisor, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |
| Apologies | Chris Moran, Commercial Manager, Castlegate Civils Ltd |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Health and safety | No incidents. | - | - | - |
| 4.2 | Earthworks | Topsoil strip 40 per cent complete between Ch 0+000 and Ch 1+400. | - | - | - |
| 4.3 | Utilities | OpenLine Telecom wayleave agreed; duct diversion in June. Earthworks resequenced. | - | - | - |
| 4.4 | River Kest Bridge | West abutment piling rig arrives 9 May. Trial mix report for deck concrete received. | - | - | - |

Initials: MB = Mark Bellamy; JK = Jo Kimani; RD = Ryan Doyle; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; CM = Chris Moran