Castlegate Civils Ltd

# Progress Meeting No. 5 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0005 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 15 May 2025 |

| Meeting date | 15 May 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; David Okafor, Project Engineer, Arden Moss Consulting Engineers; Sam Whitfield, Drainage Engineer, Arden Moss Consulting Engineers |
| Apologies | Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Health and safety | One minor hand injury reported. Glove policy re-briefed. | - | - | - |
| 5.2 | Earthworks | Earthworks between chainage 0+000 and 2+100 started on 7 April and are on programme. | - | - | - |
| 5.3 | Pond 2 East | NCC advised that the updated Mill Brook flood model may reduce the Pond 2 East discharge limit. A formal letter is expected before the next meeting. | Issue letter confirming the Pond 2 East discharge limit | HM | 29/05/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; HM = Helen Marsh; TR = Tom Reddy; DO = David Okafor; SW = Sam Whitfield; PN = Priya Nair