Castlegate Civils Ltd

# Progress Meeting No. 7 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0007 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 12 June 2025 |

| Meeting date | 12 June 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Ryan Doyle, Piling Supervisor, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |
| Apologies | David Okafor, Project Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Health and safety | No reportable incidents this period. Near miss at the haul road crossing to be briefed at toolbox talks. | Brief all operatives on the haul road crossing | JK | 19/06/2025 |
| 7.2 | Programme | Earthworks two weeks behind due to wet weather. Recovery plan to follow. | Issue recovery programme | MB | 26/06/2025 |
| 7.3 | River Kest Bridge - east abutment piling | Piling started on 9 June. At pile E3 the boring log recorded very soft grey clay from about -2 mAOD, and the design toe level of -5.15 mAOD was reached still in soft clay. Piling at the east abutment is paused. RD noted the ground does not match the GI interpretation. | Raise an RFI on east abutment pile founding level | JK | 16/06/2025 |
| 7.4 | Mill Lane culvert | Trial holes found the water main about 0.6 m deeper than the utility records, close to the culvert roof. | Write to Northvale Water with trial hole results | TR | 20/06/2025 |
| 7.5 | Pond 2 East | ADM revised drainage calculations for Pond 2 are awaited. | Confirm date for revised Pond 2 calculations | PN | 20/06/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; RD = Ryan Doyle; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; DO = David Okafor