Castlegate Civils Ltd

# Progress Meeting No. 11 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0011 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 11 September 2025 |

| Meeting date | 11 September 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Chris Moran, Commercial Manager, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers; Sam Whitfield, Drainage Engineer, Arden Moss Consulting Engineers |
| Apologies | David Okafor, Project Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 11.1 | Health and safety | No incidents this period. | - | - | - |
| 11.2 | Earthworks | Cut substantially complete. Capping in progress between Ch 2+800 and Ch 4+200. | - | - | - |
| 11.3 | Mill Lane culvert | Base slab cast. Protection works completed with the Northvale Water inspector present. | - | - | - |
| 11.4 | Pond 2 East flow control | Flow control submittal received 29 August; ADM review in progress. | - | - | - |
| 11.5 | River Kest Bridge deck | Deck waterproofing submittal due 18 September. | Submit deck waterproofing system | RD | 18/09/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; CM = Chris Moran; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; SW = Sam Whitfield; DO = David Okafor