Castlegate Civils Ltd

# Progress Meeting No. 12 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0012 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 16 October 2025 |

| Meeting date | 16 October 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Chris Moran, Commercial Manager, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers; Sam Whitfield, Drainage Engineer, Arden Moss Consulting Engineers |
| Apologies | Nadia Hussain, Highways Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 12.1 | Health and safety | No incidents this period. | - | - | - |
| 12.2 | Pond 2 East flow control | The substitute Streamflow SV-100 device (submittal P02) was rejected on 14 October as it passes 6.3 l/s. The Aqualine VFC-150 approved at P01 is to be installed. | - | - | - |
| 12.3 | Pond 2 East enlargement | Enlarged pond drawings (C02) due 20 October. Pond 2 construction to start 27 October. | Issue Pond 2 East C02 drawings | SW | 20/10/2025 |
| 12.4 | River Kest Bridge - east abutment | GA revision P03 (abutment drainage layer) issued for comment on 2 October. CGC to build to C02 until any change is issued for construction. | - | - | - |

Initials: MB = Mark Bellamy; JK = Jo Kimani; CM = Chris Moran; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; SW = Sam Whitfield; NH = Nadia Hussain