## Programme
Project | Kestrel Valley Link Road
Title | Construction Programme
Document | KVL-CGC-100-SC-G-0002
Revision | P03
Status | FI - For information
Date | 1 October 2025
Note | Pond 2 East rescheduled for the enlarged pond (5.0 l/s discharge limit).
Note | Surfacing moved to follow the Eastern Roundabout. Completion forecast 26 June 2026.
ID | Activity | WBS | Start | Finish | Duration (days)
A10 | Site clearance | 000 | 2025-03-10 | 2025-04-04 | 26
A20 | Earthworks Ch 0+000 to 2+100 | 200 | 2025-04-07 | 2025-08-08 | 124
A30 | Earthworks Ch 2+100 to 4+200 | 200 | 2025-05-05 | 2025-09-19 | 138
A40 | River Kest Bridge west abutment piling | 410 | 2025-05-12 | 2025-06-06 | 26
A50 | River Kest Bridge east abutment piling | 410 | 2025-08-11 | 2025-09-12 | 33
A60 | River Kest Bridge deck | 410 | 2025-09-29 | 2026-01-23 | 117
A70 | Mill Lane culvert | 330 | 2025-08-25 | 2025-10-24 | 61
A80 | Pond 1 West | 310 | 2025-05-19 | 2025-07-11 | 54
A90 | Pond 2 East | 320 | 2025-10-27 | 2026-01-23 | 89
A100 | Eastern Roundabout | 510 | 2025-08-04 | 2025-11-07 | 96
A110 | Surfacing | 200 | 2025-11-10 | 2026-03-27 | 138
A120 | Completion | 000 | 2026-06-26 | 2026-06-26 | 1

## Revision history
Rev | Date | Description
P01 | 01/03/2025 | Baseline programme
P02 | 26/06/2025 | Recovery programme
P03 | 01/10/2025 | Programme update