Castlegate Civils Ltd

# Request for Information

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-330-RI-S-0013 |
| Revision | P01 |
| Status | OP - Open |
| Date | 24 June 2025 |

| RFI subject | Mill Lane culvert - clash with existing water main |
| --- | --- |
| Raised by | Jo Kimani, Site Engineer, Castlegate Civils Ltd |
| Addressed to | Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |
| Response required by | 8 July 2025 |
| Programme impact | Significant - culvert excavation on hold |
| References | KVL-ADM-330-DR-S-0205, KVL-NCC-610-LT-U-0014 |

## Query

Trial holes TH1 to TH3 show the existing 300 mm water main at +13.40 mAOD, 0.30 m above the culvert roof shown on KVL-ADM-330-DR-S-0205 C01. The culvert excavation cannot proceed without undermining the main.

Please advise whether the culvert level is to be revised or the main diverted.

## Response

(To be completed by the designer.)