Castlegate Civils Ltd

Helen Marsh
Project Manager
Northvale County Council

Our ref: KVL-CGC-100-LT-G-0020
Date: 10 June 2025

Dear Helen,

Early warning - wet weather impact on earthworks

Rainfall in late May and early June was well above average. Fill placement has been suspended on 9 of the last 15 working days.

Earthworks are about two weeks behind programme. We will set out the effect on completion at the next progress meeting.

Yours sincerely,

Mark Bellamy, Project Manager, Castlegate Civils Ltd

cc: Tom Reddy, Highways Engineer, Northvale County Council; Chris Moran, Commercial Manager, Castlegate Civils Ltd