Castlegate Civils Ltd

# Progress Meeting No. 1 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0001 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 6 March 2025 |

| Meeting date | 6 March 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Kate Sorensen, Health and Safety Advisor, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; David Okafor, Project Engineer, Arden Moss Consulting Engineers |
| Apologies |  |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Health and safety | Construction phase plan issued 28 February. Site induction in place. | - | - | - |
| 1.2 | Mobilisation | Site compound set up at Mill Lane. Welfare facilities complete. | - | - | - |
| 1.3 | Programme | Programme issued 1 March. Site clearance starts 10 March. | Confirm site clearance sequence | JK | 20/03/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; KS = Kate Sorensen; HM = Helen Marsh; TR = Tom Reddy; DO = David Okafor