Castlegate Civils Ltd

# Progress Meeting No. 2 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0002 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 20 March 2025 |

| Meeting date | 20 March 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; David Okafor, Project Engineer, Arden Moss Consulting Engineers; Rachel Ames, Senior Ecologist, Arden Moss Consulting Engineers |
| Apologies | Kate Sorensen, Health and Safety Advisor, Castlegate Civils Ltd |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Health and safety | No incidents. | - | - | - |
| 2.2 | Vegetation clearance | Method statement accepted on 12 March. Clearance to finish by 31 March, outside the bird nesting season. Tree T31 on Mill Lane is retained. | - | - | - |
| 2.3 | Ecology | Amphibian fencing near field pond FP1 installed; trapping under way. | Confirm completion of newt trapping | RA | 03/04/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; HM = Helen Marsh; TR = Tom Reddy; DO = David Okafor; RA = Rachel Ames; KS = Kate Sorensen