Castlegate Civils Ltd

# Request for Information

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-410-RI-S-0012 |
| Revision | P01 |
| Status | OP - Open |
| Date | 16 June 2025 |

| RFI subject | East abutment piles - soft clay below founding level |
| --- | --- |
| Raised by | Jo Kimani, Site Engineer, Castlegate Civils Ltd |
| Addressed to | Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |
| Response required by | 30 June 2025 |
| Programme impact | Significant - east abutment piling stopped |
| References | KVL-ADM-410-DR-S-0102, KVL-ADM-410-DR-S-0110, KVL-SGI-410-RP-T-0001 |

## Query

During boring of pile E3 at the east abutment, very soft grey clay was encountered from approximately -2.0 mAOD and continued below the design toe level of -5.15 mAOD shown on drawings KVL-ADM-410-DR-S-0102 C01 and KVL-ADM-410-DR-S-0110 C01.

Please confirm a revised pile founding level and pile length for the east abutment piles, and whether temporary casing is required through the soft clay.

## Response

(To be completed by the designer.)