Castlegate Civils Ltd

# Progress Meeting No. 6 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0006 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 29 May 2025 |

| Meeting date | 29 May 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Chris Moran, Commercial Manager, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; David Okafor, Project Engineer, Arden Moss Consulting Engineers; Sam Whitfield, Drainage Engineer, Arden Moss Consulting Engineers; Nadia Hussain, Highways Engineer, Arden Moss Consulting Engineers |
| Apologies | Tom Reddy, Highways Engineer, Northvale County Council |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Health and safety | No incidents this period. | - | - | - |
| 6.2 | Pond 2 East | NCC letter of 22 May received - Pond 2 East discharge limit reduced from 8.0 l/s to 5.0 l/s. ADM to assess the extra storage needed. Pond 2 construction to be held. | Revise Pond 2 attenuation design | SW | 31/07/2025 |
| 6.3 | Eastern Roundabout surfacing | CM flagged a national shortage of high PSV aggregate. Supply of PSV 68 for the roundabout surface course is at risk. | Confirm aggregate supply dates | CM | 12/06/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; CM = Chris Moran; HM = Helen Marsh; DO = David Okafor; SW = Sam Whitfield; NH = Nadia Hussain; TR = Tom Reddy