Castlegate Civils Ltd

# Progress Meeting No. 8 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0008 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 26 June 2025 |

| Meeting date | 26 June 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Ryan Doyle, Piling Supervisor, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers |
| Apologies | David Okafor, Project Engineer, Arden Moss Consulting Engineers |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 8.1 | Health and safety | No incidents this period. | - | - | - |
| 8.2 | Programme | Recovery programme issued today (revision P02). Completion now forecast 29 May 2026. | - | - | - |
| 8.3 | River Kest Bridge - east abutment piling | RFI-0012 on the soft clay remains open. ADM response due 30 June. Piling paused. | - | - | - |
| 8.4 | Mill Lane culvert | RFI-0013 raised on 24 June for the clash with the water main. Awaiting Northvale Water's requirements. | Respond to RFI-0013 once Northvale Water has replied | PN | 15/07/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; RD = Ryan Doyle; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; DO = David Okafor