Castlegate Civils Ltd

# Progress Meeting No. 9 - Minutes

| Project | Kestrel Valley Link Road |
| --- | --- |
| Document | KVL-CGC-100-MM-G-0009 |
| Revision | P01 |
| Status | IS - Issued |
| Date | 17 July 2025 |

| Meeting date | 17 July 2025 |
| --- | --- |
| Location | Castlegate site office, Kestrel Valley |
| Chair | Mark Bellamy, Project Manager, Castlegate Civils Ltd |
| Present | Mark Bellamy, Project Manager, Castlegate Civils Ltd; Jo Kimani, Site Engineer, Castlegate Civils Ltd; Chris Moran, Commercial Manager, Castlegate Civils Ltd; Helen Marsh, Project Manager, Northvale County Council; Tom Reddy, Highways Engineer, Northvale County Council; Priya Nair, Lead Bridge Engineer, Arden Moss Consulting Engineers; Nadia Hussain, Highways Engineer, Arden Moss Consulting Engineers |
| Apologies | Ryan Doyle, Piling Supervisor, Castlegate Civils Ltd |

| Item | Subject | Discussion | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| 9.1 | Health and safety | No incidents this period. | - | - | - |
| 9.2 | River Kest Bridge - east abutment piling | ADM response to RFI-0012 issued 30 June - piles lengthened to 24 m. C02 drawings issued 10 July. | - | - | - |
| 9.3 | Mill Lane culvert | Northvale Water replied on 8 July - 600 mm clearance required; a protection slab is acceptable in principle. ADM response to RFI-0013 issued 15 July. | - | - | - |
| 9.4 | Eastern Roundabout surfacing | CGC letter of 2 July proposed PSV 65 aggregate. Submittal issued 10 July, awaiting ADM review. | Review alternative aggregate submittal | NH | 31/07/2025 |

Initials: MB = Mark Bellamy; JK = Jo Kimani; CM = Chris Moran; HM = Helen Marsh; TR = Tom Reddy; PN = Priya Nair; NH = Nadia Hussain; RD = Ryan Doyle